## Product Backlog
Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
Sprint 1 | 2026-02-01 | 2026-02-14 | Rishika | Implementing structured error handling for Flask APIs | Hardcoding secret keys in source code | Using SQLite for rapid development | Add environment variable validation at startup
Sprint 1 | 2026-02-01 | 2026-02-14 | Tej | Adding loading indicators for ticket submission | Ignoring frontend validation | Using fetch API for backend communication | Add comprehensive client-side validation
Sprint 1 | 2026-02-01 | 2026-02-14 | Sekar | Adding confidence scores to ML predictions | Relying only on model output without fallback | Implementing rule-based classification fallback | Improve preprocessing and model tuning
Sprint 1 | 2026-02-01 | 2026-02-14 | Ranji | Creating database indexes for faster ticket queries | Manual database edits during runtime | Regular database backups | Automate schema initialization on startup
Sprint 1 | 2026-02-01 | 2026-02-14 | Praveen | Setting up local deployment workflow | Manual testing of each API repeatedly | Monitoring API performance | Add health-check endpoint for backend
Sprint 1 | 2026-02-01 | 2026-02-14 | Rishika | Implementing input validation for ticket forms | Logging sensitive user input | Regular security checks | Add rate limiting to ticket submission API
Sprint 1 | 2026-02-01 | 2026-02-14 | Tej | Conducting usability testing for ticket UI | Making UI changes without testing | Maintaining consistent design patterns | Create reusable UI components
Sprint 2 | US-008 | As an agent, I want to reassign tickets to other agents when needed |  | US-003 |  | Completed
Sprint 2 | US-009 | As a user, I want to export my ticket history for personal records | WON'T | US-001 |  | Completed
Note on E1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 45 | 9 | 6 | 4 | 7 | 6 | 3 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T001-1 | Design Flask API routes for ticket creation | 2026-02-01 | 2026-02-01 |  | Development | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T001-2 | Document API endpoints | 2026-02-01 | 2026-02-01 |  | Documentation | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T002-1 | Create frontend ticket submission form | 2026-02-02 | 2026-02-02 |  | Development | Completed | 4 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T002-2 | Add form validation and error messages | 2026-02-02 | 2026-02-02 |  | Development | Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T003-1 | Design SQLite ticket database schema | 2026-02-01 | 2026-02-01 |  | Development | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T004-1 | Train initial ticket classification model | 2026-02-03 | 2026-02-03 |  | Development | Completed | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T004-2 | Create prediction function for category & priority | 2026-02-04 | 2026-02-04 |  | Development | Completed | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T005-1 | Implement rule-based fallback logic | 2026-02-05 | 2026-02-05 |  | Development | Completed | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T006-1 | Design dashboard layout for ticket viewing | 2026-02-04 | 2026-02-04 |  | Design | In Progress | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T006-2 | Implement ticket list display component | 2026-02-05 | 2026-02-05 |  | Development | Completed | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T007-1 | Connect frontend with Flask backend APIs | 2026-02-06 | 2026-02-06 |  | Development | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T007-2 | Store submitted tickets in database | 2026-02-06 | 2026-02-06 |  | Development | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T008-1 | Integrate AI predictions with ticket creation flow | 2026-02-07 | 2026-02-07 |  | Development | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T008-2 | Test end-to-end ticket submission workflow | 2026-02-07 | 2026-02-07 |  | Testing | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Initial SQLite database connection setup | Configured SQLite connection and verified local DB access
Sprint 1 | Day 1 | Environment variable configuration | Created .env file for secret keys and database path
Sprint 1 | Day 2 | CORS issue between frontend and Flask | Enabled CORS in Flask using flask-cors
Sprint 1 | Day 2 | API endpoint structure confusion | Defined REST API routes for ticket creation and retrieval
Sprint 1 | Day 3 | Model loading delay during startup | Implemented lazy loading for ML model
Sprint 1 | Day 3 | Frontend form validation errors | Added client-side validation and error prompts
Sprint 1 | Day 4 | Database write failure for new tickets | Fixed schema mismatch and commit handling
Sprint 1 | Day 4 | Low AI classification accuracy | Tuned preprocessing and improved fallback rules
Sprint 1 | Day 5 | Frontend not receiving API response | Fixed JSON response handling and fetch logic
Sprint 1 | Day 5 | Dashboard layout breaking on small screens | Added responsive CSS adjustments

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-01 | 2026-02-14 |  | Implementing structured error handling for Flask APIs | Hardcoding secret keys in source code | Using SQLite for rapid development | Add environment variable validation at startup
2 | Sprint 1 | 2026-02-01 | 2026-02-14 |  | Adding loading indicators for ticket submission | Ignoring frontend validation | Using fetch API for backend communication | Add comprehensive client-side validation
3 | Sprint 1 | 2026-02-01 | 2026-02-14 |  | Adding confidence scores to ML predictions | Relying only on model output without fallback | Implementing rule-based classification fallback | Improve preprocessing and model tuning
4 | Sprint 1 | 2026-02-01 | 2026-02-14 |  | Creating database indexes for faster ticket queries | Manual database edits during runtime | Regular database backups | Automate schema initialization on startup
5 | Sprint 1 | 2026-02-01 | 2026-02-14 |  | Setting up local deployment workflow | Manual testing of each API repeatedly | Monitoring API performance | Add health-check endpoint for backend
6 | Sprint 1 | 2026-02-01 | 2026-02-14 |  | Implementing input validation for ticket forms | Logging sensitive user input | Regular security checks | Add rate limiting to ticket submission API
7 | Sprint 1 | 2026-02-01 | 2026-02-14 |  | Conducting usability testing for ticket UI | Making UI changes without testing | Maintaining consistent design patterns | Create reusable UI components